## Sheet1
ID | Module | UI Element / Flow | PRD Requirement (short) | Architecture Mapping | Interaction / Accessibility | Telemetry / KPI | Status | Owner | Notes
UI-001 | Landing | Ask Your CPO input → Enter submits to Advisor | PRD v4.0 §2 (Scope: Landing Page) + §5 (Accessibility: Enter=submit) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §1 (System Overview) + §3.1 (Accessibility Playbook) + §4.1 (Response Contract) (docs/Architecture/Architecture_v4.1.md) | Keyboard: Enter=submit; Focus ring 2px Indigo-300 | TTFA (time_to_first_answer_ms) | Compliant
UI-002 | Landing | Module buttons → navigate to dashboards (HR Analytics, Engagement, Performance) | PRD v4.0 §2 (Scope: Landing Page – Module Tiles) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §1.1 (Conceptual Diagram) (docs/Architecture/Architecture_v4.1.md) | Button hover/active; focus visible | Click-through events per module | Compliant
UI-010 | Advisor | Typing indicator while model responds | PRD v4.0 §4 (Functional Requirements: Advisor – Typing indicators) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §4.2 (Streaming & UX Hooks: SSE typing indicator) (docs/Architecture/Architecture_v4.1.md) | Skeleton/typing indicator pattern | TTFA; response_stream_duration_ms | Compliant
UI-011 | Advisor | Responses include citations & 'Why this looks like this' tag | PRD v4.0 §4 (Advisor: Responses include sources + explainability tags) + §11 (Success Metrics ≥95% citations) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §4.1 (Response Contract: citations[], explainability_tag) + §9 (Telemetry KPIs) (docs/Architecture/Architecture_v4.1.md) | Toast on failure + retry | citation_rate >= 95% | Compliant
UI-012 | Advisor | Prompt Rail (always-visible suggested prompts) | PRD v4.0 §2 (Scope: Advisor – Suggested prompts always visible) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §3.3 (App Shell & Patterns: Prompt Rail mandated) (docs/Architecture/Architecture_v4.1.md) | Keyboard focusable chips | Prompt chip engagement rate | Compliant
UI-020 | Dashboards – Global | 2x2 chart grid; each card has Title, Legend, Tooltip, AI Insights | PRD v4.0 §2 (Scope: Dashboards) + §4 (Functional: Charts with legends, AI Insights) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §5.1 (Chart Models: eNPS, 9-box) + §5.2 (Endpoints) (docs/Architecture/Architecture_v4.1.md) | Hover tooltips; keyboard focusable data points if applicable | dashboard_render_ms p95 < 10000 | Compliant
UI-021 | Dashboards – Global | Upload Data + Export Data actions | PRD v4.0 §4 (Dashboards: Empty state 'Upload a CSV to see insights.') (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §3.3 (App Shell: Empty State pattern) + §5 (Dashboards Service) (docs/Architecture/Architecture_v4.1.md) | Retry banners on failure; success toasts | upload_error_rate; export_success_rate | Compliant
UI-030 | HR Analytics | Demographic breakdown (gender/race), attrition | PRD v4.0 §2 (Engagement Module: survey summaries, eNPS) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §5.1 (eNPS Chart Contract) (docs/Architecture/Architecture_v4.1.md) | Legends accessible; color mapping consistent | data_coverage_pct | Compliant
UI-040 | Employee Engagement | eNPS visualization | PRD v4.0 §2 (Performance Module: review cycle, 9-box) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §5.1 (9-box Chart Contract) (docs/Architecture/Architecture_v4.1.md) | Tooltip explains eNPS formula | enps_response_rate; enps_score | Compliant
UI-050 | Performance Analysis | 9-box performance distribution | PRD v4.0 §2 (PIP Builder: Stepper flow, AI suggestions, quick actions) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §6 (Builders State Machines) (docs/Architecture/Architecture_v4.1.md) | Keyboard navigation between cells; tooltip on bin | underperformer_pct; promotion_rate | Compliant
UI-060 | PIP Builder | Form + Advisor aligned; stepper removed; export branded PIP | PRD v4.0 §2 (JD Builder: Stepper flow, structured sections, Advisor quick actions) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §6 (Builders State Machines) (docs/Architecture/Architecture_v4.1.md) | Inline validation; error summaries | export_success_rate; time_to_draft | Compliant |  | Resolution: JD Builder form + Advisor + branded export - PRD: enforce Advisor panel + quick actions; branded export rules (logo/header/footer/watermark). - Arch: Builders state machine persists drafts; Advisor contract (citations/explainability_tag); Export Engine brand checks. - UI: Stepper with draft editor + inline suggestions; tokenized colors/typography; export via /v1/export/pdf. - QA: E2E test (upload→draft→advisor→export); verify branding and font embedding; snapshot exports. - Telemetry: link trace_id from Advisor to export; log export_branding_compliance.
UI-061 | JD Builder | Form + Advisor aligned; export branded JD | State machine; structured sections (Overview, Responsibilities…) | Builders service; Export Engine | Autosave; undo | export_success_rate; completion_time | Needs review
UI-070 | Exports | Branded layouts: header logo left, client name right; footer text; watermark | PRD v4.0 §4 (Dashboards + Builders: Exports PDF/CSV/XLSX branded) + §11 (Success Metrics: branding rules) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §7 (Export Engine: Branding rules, APIs) (docs/Architecture/Architecture_v4.1.md) | High-contrast text; pdf metadata | export_branding_compliance | Compliant
UI-080 | Accessibility | Keyboard: Enter=submit, Esc=close; predictable tab order | PRD v4.0 §5 (Non-Functional: Accessibility enforceable, contrast, ARIA, focus ring) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §3.1 (Accessibility Playbook) (docs/Architecture/Architecture_v4.1.md) | 2px Indigo-300 focus ring on all focusable | a11y_violations_per_release | Compliant |  | Resolution: Accessibility (contrast ≥4.5:1; ARIA roles; focus ring) - PRD: acceptance criteria enforceable; focus ring 2px Indigo-300. - Arch: a11y playbook + CI gates (axe-core/pa11y + Playwright keyboard tests for Enter/Esc + tab order). - UI: Roles on nav/main/form/button/alert; tokens for contrast; no focus trapping except modals. - QA: Lint with eslint-plugin-jsx-a11y; visual contrast checks; Storybook a11y add-on; golden screenshots. - Release gate: block merge if a11y suite fails.
UI-081 | Accessibility | Contrast ratio ≥4.5:1; ARIA roles (nav, main, form, button, alert) | Accessibility is enforceable; acceptance criteria in PRD | Linting and visual tests; roles in components |  | Needs review
UI-090 | Empty States | Dashboards: “Upload a CSV to see insights” | PRD v4.0 §11 (Success Metrics: TTFA <10s, ≥95% citation rate, dashboard render <10s) (docs/PRD/PRD_v4.0.pdf) | Arch v4.1 §9 (Telemetry & KPIs) (docs/Architecture/Architecture_v4.1.md) | Focusable Upload CTA | empty_to_active_conversion_rate | Compliant